## LOG
PROG280 Final Project Log
Task | Feature | Status | Duration | Description | Comments
Design Forms | Basic Functionality | In-Progress | 2 hours | Designing the forms to display controls for the user | Created the starting form with buttons to begin types of games, added background images to both the starting form and the game board form.
Create AI | Offline Functionality | In-Progress | 30 mins | Create an AI player to compete with the player offline | Created basic "dealer rules" AI that stands on 17 or higher and hits below that.
Create TCP Connection | Basic Functionality | Not-Started |  | Establish a connection between players
Create User Classes | User Accounts | Not-Started
Create Card/Deck Classes | Basic Functionality | In-Progress | 30 mins | Add classes to manage the cards in a deck and shuffle them for randomization. | Created card class with constructor, created deck with option to add cards and method to shuffle the deck.
Create Dealing Cards Methods | Basic Functionality | In-Progress | 1 hour

## EXAMPLE
PROG280 Final Project Log - EXAMPLE
Task | Feature | Status | Duration | Description | Comments
Implement transparent image support | Chat | Completed | 30 minutes | Wasn't that hard I found an example on codeproject | 10/10 would not do this again
Add emoji support | Chat | Abandonned | 5 hours | No one even likes emojis | This is a debatable topic but I decided to scrap the feature
Additional TCP connection for sharing screen image | Meeting | In-Progress | ~1 hour so far | An additional connection will be created so the images do not disrupt the chat functionality | Works okay but UDP may have alleviated bandwidth issues
Request control | Remote Control | Not-Started |  | Allow a user to request control from the host PC | Struggling on where to begin this task