## LOG
PROG280 Final Project Log
Task | Feature | Status | Duration | Description | Comments
Design Forms | Basic Functionality | Finished | 1 hour | Designing the forms to display controls for the user | Completed the remaining elements of the forms to allow for the chat and game functions to be displayed correctly.
Create AI | Offline Functionality | Finished | 30 minutes | Create an AI player to compete with the player offline | Game seems to operate as intended.
Create TCP Connection | Basic Functionality | In-Progress | 1 hour | Establish a connection between players | Majority of connection is complete, however the user scores get out of sync after long matches and disconnecting does not shut down the TCP listener.
Send Game Challenge via Chat | Basic Functionality | In-Progress | 30 minutes | Allow a user to send a challenge via the chat system to initiate a game between players | Almost complete, need to create a method that allows the user to track their challenges to prevent issuing multiple to the same user, and a method to remove them when declined.
Create connection between players for game | Basic Functionality | In-Progress | 2 hours | Allow the host to send cards and information to the client to play a game of blackjack. | Most functionality working, some confusing disparities between scores of users over long matches.

## EXAMPLE
PROG280 Final Project Log - EXAMPLE
Task | Feature | Status | Duration | Description | Comments
Implement transparent image support | Chat | Completed | 30 minutes | Wasn't that hard I found an example on codeproject | 10/10 would not do this again
Add emoji support | Chat | Abandonned | 5 hours | No one even likes emojis | This is a debatable topic but I decided to scrap the feature
Additional TCP connection for sharing screen image | Meeting | In-Progress | ~1 hour so far | An additional connection will be created so the images do not disrupt the chat functionality | Works okay but UDP may have alleviated bandwidth issues
Request control | Remote Control | Not-Started |  | Allow a user to request control from the host PC | Struggling on where to begin this task